## Sheet1
CLIENT: | POWERADE RUN BARBADOS 2014
DELIVERABLE: | MARKETING COMMUNICATIONS GANTT CHART
PROGRAMME DATES: | November 9 - December 6, 2014
FACEBOOK ADS |  |  |  | November | [20 empty] | December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Target: 2,000 total page likes; Reach: 130,000 persons: Demographic: Locals aged 16 - 65. (Ads will be increasingly targeted to persons interested in fitness, running, etc. based on performance). |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Objective | Message | Budget (BDS $) | Subtotal (BDS $)
Page Likes | Come for the Run! Stay for the Fun! | 250 | bar: November S 9 to November S 22
Post Engagement | POWERade Fun Mile | 100 | bar: November S 23 to December S 30
Post Engagement | Race Count Down | 150 | 500 | bar: December S 30 to December T 4
GOOGLE ADVERTISEMENTS |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Target: Keywords - persons who use keywords such as “Barbados”, “Barbados Marathon”, “Barbados 10K”, “Run Barbados”, etc.; Display: Tablets, mobiles and desktop computers being using in Barbados. |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Objective | Message | Budget (BDS $) | Subtotal (BDS $)
Increase awareness and encourage registration | Come for the Run! Stay for the Fun! | 300 | bar: November W 12 to December S 7
Increase awareness and increase residual registration | POWERade Fun Mile | 100 | 400 | bar: November M 24 to December F 5
EMAIL BLASTS |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Target: Internet savvy Barbadians of all strata who rely regularly on online communication for instant news and information updates. |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Channel | Message | Budget (BDS $) | Subtotal (BDS $)
Tell Barbados | Come for the Run! Stay for the Fun! | 500 | bar: November W 12; November M 17; November F 21; November W 26; December T 4
| CEO Challenge | 200 | bar: November W 12; November M 17
| POWERade Fun Mile | 300 | 1000 | bar: November F 14; November W 26; December T 4
Impressions Barbados | Message | Budget (BDS $) | Subtotal (BDS $)
| Come for the Run! Stay for the Fun! | 450 | bar: November W 12; November M 17; November F 21; November W 26; December W 3
| CEO Challenge | 180 | bar: November W 12; November M 17
| POWERade Fun Mile | 270 | 900 | bar: November W 19; November W 26; December T 2
PRESS ADS |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Target: Barbadians aged 25 - 60 who rely on the daily print media for news updates. |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Channel | Size | Budget (BDS $) | Subtotal (BDS $)
Barbados Advocate | 14x3/ 14" x 5.25"/ Colour | 2636.23 | bar: November S 23
Business Monday | 10x4/ 10" x 7"/ Colour | 4326.34 | 13925.14 | bar: November M 17; November M 24
Mid-week Nation | 10x4/ 10" x 7"/ Colour | 2524.37 | bar: November W 12
Sunday Sun | 10x4/ 10" x 7"/ Colour | 7076.32 | bar: November S 16; December S 30
Business Authority | 10x4/ 10" x 7"/ Colour | 3044.66 | bar: November M 17; November M 24
Website Ad | 0.94h x 7.58w/ One Month | 1051.625 | bar: November M 17 to December S 7
Weekend Nation | Full Page Full Colour | 4802.27 | bar: November F 21
Newspaper Insert/ Sunday Sun | 8.5"x11"/ $240x25K | 9987.5 | bar: November S 23
Weekend Nation | 10x4/ 10" x 7"/ Colour | 4802.27 | 33289.015 | bar: November F 28
Barbados Today | 10x4/ 10" x 7"/ Colour | 835.66 | 2506.98 | bar: November W 12; November W 19; November W 26
RADIO ADS |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Target: Barbadians of various age groups with interests ranging from popular culture to call-in programmes and news and current affairs. Ads will be targeted where possible to cater to the varying audiences. |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
STATION | AD SIZE/ FREQUENCY | Budget (BDS $) | Subtotal (BDS $)
VOB 92.9 FM | Prime time/ 30-second * 3 daily spots | 7644.78 | bar: November T 13 to November F 14; November M 17; November W 19; November F 21; November T 25; November T 27; November S 29 to December F 5
HOTT 95.3 FM | Prime time/ 30-second * 2 daily spots | 2376 | bar: November T 13; November S 15; November M 17; November W 19; November F 21; November M 24; November W 26; November F 28 to November S 29; December M 1; December T 4 to December F 5
LOVE 104.1 FM | Prime time/ 30-second * 2 daily spots | 1485 | bar: November F 14; November M 17; November F 21; November M 24; November W 26; November F 28; December T 2; December T 4 to December F 5
SLAM 101.1 FM | Prime time/ 30-second * 2 daily prime time spots | 2115 | bar: November F 14 to November S 15; November F 21 to November S 22; November W 26; November F 28 to November S 29; December T 2; December T 4 to December F 5
THE ONE 98.1 FM | Prime time/ 30-second * 2 daily spots | 1809.5 | 15430.28 | bar: November F 14 to November S 15; November F 21 to November S 22; November W 26; November F 28 to November S 29; December T 2; December T 4 to December F 5
RADIO PROGRAMMES |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Target: Barbadians of various age groups with interests ranging from popular culture to call-in programmes and news and current affairs. Ads will be targeted where possible to cater to the varying audiences. |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
STATION | PROGRAMME LENGTH/ FREQUENCY | Budget (BDS $) | Subtotal (BDS $)
VOB 92.9 FM | Seven 5-minute programmes | 1680 | bar: November F 14; November M 17; November W 19; November F 21; November M 24; November W 26 to November T 27
VOB 92.9 FM | Live Race Coverage | TBD
Y 103.3 FM (with Runner Carlie Pipe) | One Radio Half Hour/ Morning Show | 705 | 2385 | bar: November F 21
OUTDOOR BANNERS |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
To alert persons traversing high traffic areas of the impending series dates. |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Outdoor Banners | Two 4x4 Billboards | 1500 | 1500 | bar: November F 21 to December M 8
VIDEO MESSAGES |  |  |  | November S 9: November; December S 30: December
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Avid runners and running enthusiasts to share 1-minute videos on what running means to them |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Video Endorsements for social media | 10X 30-second videos | 2000 | 2000 | bar: November F 21 to December S 30
TOTAL |  |  | 73836.415
NOTES
VOB prices are worst case scenario; VOB to confirm a discounted package totally $7000 including 20 two-minute flashes starting next week, inclusive on one mention and one commercial; as well as 3 hours live coverage of the half marathon and the POWERade 10K; and 30 second spots.
Y103.3 half hour was included as the host for the show is a well-known runner, who is also recommended for the videos.
Nation Ads can be replaced by 1/4 pages to cut cost but won't have the impact. The insert is a ' nice-to-have' though it would be impactful .